# Project Phoenix — Weekly Steering Meeting

Attendees: Project Team, Operations Lead, Finance

# Schedule

Phase 2 commissioning is tracking two weeks behind baseline due to a delayed grid connection permit.

# Agreed actions

Project team to submit the revised grid connection application within one week.

Finance to review the monthly energy report and confirm the revised budget forecast.

Operations to schedule the WTG-3 gearbox inspection alongside crane mobilisation.

# Risks

If the permit is not granted within three weeks, Phase 2 revenue moves to the next quarter. Mitigation: escalate to the regulator.