Q3 Operations Review — Meeting Minutes

Coastal Ridge Wind Farm — September 15, 2026

# Meeting Details

| Field | Detail |
| --- | --- |
| Date / Time | September 15, 2026, 10:00–12:00 |
| Location | Site Operations Office / Video conference |
| Chair | R. Okafor, Site Operations Manager |
| Minutes taken by | T. Nwosu, Operations Coordinator |

## Attendees

R. Okafor — Site Operations Manager (Chair)

J. Alvarez — Mechanical Maintenance Lead

S. Whitfield — Electrical Maintenance Lead

D. Petrov — Health & Safety Officer

M. Chen — VP Operations (remote)

L. Ferreira — Finance Business Partner

K. Osei — Procurement Lead

# 1. Fleet Performance Review

R. Okafor opened with the Week 37 performance summary: fleet availability at 96.2%, down from 98.1% the prior week, driven primarily by Turbine T-19 being taken offline. Energy delivered was 4,180 MWh against a 4,350 MWh forecast. The group noted that excluding the T-19 outage, fleet performance was in line with seasonal expectations.

# 2. Turbine T-19 Gearbox Escalation

J. Alvarez presented the findings from the Week 37 maintenance report: three consecutive above-threshold vibration readings on T-19, a borescope inspection showing early-stage gear tooth pitting, and the OEM's recommendation of a full gearbox replacement rather than field repair. K. Osei confirmed the OEM's quoted lead time of 14 weeks for standard shipping, versus an expedited air-freight option that would reduce the lead time to approximately 4 weeks at an additional cost.

L. Ferreira presented a cost exposure estimate: each week T-19 remains offline represents approximately $15,000 in lost generation revenue at current power purchase agreement rates, meaning the 10-week difference between expedited and standard shipping represents roughly $150,000 in avoided losses, against an estimated expedite premium of $22,000.

DECISION: The group approved emergency capital expenditure of $85,000 for the T-19 gearbox replacement unit itself, and directed Procurement to proceed with the expedited air-freight shipping option. M. Chen (VP Operations) will formally sign off the capital expenditure request; Finance requires this signature by September 18, 2026 to lock in the OEM's expedited production slot. T-19 will remain offline until the replacement is installed and re-commissioned, currently estimated for mid-October.

# 3. Safety Update — Turbine T-22 Near-Miss

D. Petrov briefed the group on the near-miss reported during the Week 37 inspection at Turbine T-22, where a technician found a loose internal fall-arrest anchor bolt after having briefly clipped into it. D. Petrov noted that while this specific bolt was re-torqued and re-inspected the same day, the incident raises a broader concern about anchor-point inspection frequency across the fleet, since the current procedure only requires a visual check rather than a torque check before each climb.

DECISION: The group approved a revised site-wide policy requiring a physical torque-check of both primary and backup anchor points before every climb, effective immediately, and a full anchor-point re-certification audit of all 36 turbines to be completed by September 25, 2026. All climbing technicians must complete a refresher briefing on the new procedure before their next climb. D. Petrov will issue an updated safety bulletin (see the accompanying Safety Procedure document) and track completion of refresher briefings.

# 4. Q4 Budget Planning — Preview

L. Ferreira gave an early preview of Q4 budget planning, noting that the T-19 emergency expenditure will need to be absorbed against the maintenance contingency line rather than deferred capital projects. A full Q4 budget proposal will be circulated ahead of the October operations review.

# 5. Vendor Contract Renewal

K. Osei flagged that the site's primary spare-parts supplier contract is up for renewal in November, and that recent experience with the T-19 gearbox lead time suggests the site should negotiate guaranteed expedite terms into the renewed contract rather than treating air-freight as an ad-hoc surcharge. K. Osei will bring a renewal proposal to the October meeting.

# 6. Staffing & Training

S. Whitfield reported that two new electrical technicians completed onboarding this week and will begin supervised field work starting September 22. R. Okafor noted that the new anchor-point refresher training (Section 3) should be incorporated into the standard onboarding checklist going forward, not just issued as a one-off bulletin.

# Decisions Log

| # | Decision | Owner |
| --- | --- | --- |
| D-1 | Approve $85,000 capital expenditure for T-19 gearbox replacement | M. Chen |
| D-2 | Proceed with expedited air-freight shipping for T-19 parts | K. Osei |
| D-3 | Mandate physical torque-check of anchor points before every climb | D. Petrov |
| D-4 | Incorporate anchor-point refresher into standard onboarding | S. Whitfield |

# Action Items

| Owner | Action | Deadline | Priority |
| --- | --- | --- | --- |
| M. Chen | Sign off T-19 emergency capital expenditure request | 2026-09-18 | Critical |
| K. Osei | Confirm expedited air-freight booking with gearbox OEM | 2026-09-19 | Critical |
| D. Petrov | Issue updated anchor-point safety bulletin site-wide | 2026-09-17 | High |
| D. Petrov | Complete full anchor-point re-certification audit | 2026-09-25 | High |
| L. Ferreira | Circulate Q4 budget proposal ahead of October review | 2026-10-05 | Medium |
| K. Osei | Bring spare-parts vendor renewal proposal to October meeting | 2026-10-10 | Medium |

# Next Meeting

The next Operations Review is scheduled for October 13, 2026, 10:00, same location. Standing agenda item: T-19 gearbox replacement progress update.